## PI
PI Nr. | Story | In Date | Start Date | End Date | Impl. Days | Status | Comment | Carry-Over
PI 1 | Side / Drawer Menu Concept | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done | Think about large / very large screens | GetDateTime
| Shared Preferences Concept | 2022-12-25 | 2022-12-25 |  |  | Processing | Not working on Web | AboutDialog
| Settings Menu Concept | 2022-12-25 | 2023-01-03 |  |  | Processing |  | StartDialog
| User Management | 2022-12-25 | 2023-04-01 | 2023-05-01 |  | Done
| Club Management | 2022-12-25 | 2023-04-01 |  |  | Processing
| Light / Dark Mode Concept | 2022-12-25 | 2022-12-25 |  | -44920 | Processing | Colors set while theme set open
| Splash Screens | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done | Web is open
| Startup Warning Dialog | 2022-12-25 | 2022-12-28 | 2022-12-28 | 0 | Done
| Exit confirmation | 2022-12-25 | 2022-12-28 | 2022-12-28 | 0 | Done
| About Dialog | 2022-12-25 | 2022-12-26 | 2022-12-26 | 0 | Done | Font size depending on screen size open
| Github Repo | 2022-12-25
12.07.2023 | AccountManage, AppAction, FSA: club_manager IU, GetClubsRolesActionsResponse
13.07.2023 | requestedActions as List<String> from App => Web => convert into List<AppActions> => check resolution => return to App
Next: implement actions for browsing club (get basic info, get user list, add / remove user etc)

## Roles
| Root | Owner | Manager | Member | Guest
Create Club | O | X | X | X | O
Read Club Base Info | X | X | X | X | X
Get Club Members List | X | X | X | X | O
Edit Club Base Info | X | X | O | O | O | Club name, comment, visibility
Get Club Members | X | X | X | X | O
ChangeClubPassword | X | X | X | O | O
Hand-over Club | X | X | O | O | O | If club has multiple owners, they shall confirm (process TBD)
Join Club | O | X | X | X | O
Leave Club | O | O | X | X | O
Delete Club | X | X | O | O | O | If club has multiple owners, they shall confirm (process TBD)
Assign Owner | X | X | O | O | O
Unassign Owner | X | O | O | O | O
Assign Manager | X | X | O | O | O
Unassign Manager | X | X | O | O | O
Remove Manager | X | X | O | O | O
Invite Member | X | X | X | O | O
Remove Member | X | X | X | O | O
Create Checklist | X | X | X | O | O
Edit Checklist | X | X | X | O | O
Read Checklist | X | X | X | X | X | if visibility setting allows
Hand-over Checklist | X | X | X | O | O
Create Model | X | X | X | O | O
Edit Model | X | X | X | O | O
Read Model | X | X | X | X | X | if visibility setting allows
Hand-Over Model | X | X | X | O | O
Create Aircraft | O | X | X | O | O
Edit Aircraft | X | X | X | O | O
Read Aircraft | X | X | X | X | X | if visibility setting allows
Hand-over Aircraft | X | X | X | O | O

## Tech Debts
Function | Sub-Function | Debt | Prio | Complexity | API Ver | In Date | Start Date | End Date | Impl. Days | Status | Comment
Light / Dark Mode |  |  | B | normal |  | 2022-12-25 | 2022-12-26 |  | -44921 | Processing
Splash Screen | Web |  | B | normal |  | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Open
| Android 12+ |  | B | normal |  | 2023-01-14 |  |  | 0 | Processing
| IOS |  | B | normal |  | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done
Get Current Date / Time |  | Move to future provider as stream | B | normal |  | 2023-01-14 | 2023-01-14 | 2023-01-14 | 0 | Done
Sig-in |  | Refactor Menu | B | normal |  | 2023-01-14 |  |  | 0 | Open
|  | Use-case if user is already signed in (user / club) | B | normal |  | 2023-01-14 |  |  | 0 | Done
Font Size in Widgets |  | Switch to Theme Style with delta Size | A | normal |  | 2023-01-14 | 2023-02-01 |  |  | Open
Routing to Sign-In |  | Go to Sign-in form in case of 401 response | B | normal |  | 2023-02-26 |  |  |  | Open
Tab order, skip icon button |  | Skip icon buttons for navigation in form | B | normal |  | 2023-02-26 |  |  |  | Processing

## Login Type
Register |  | Active Login |  | Auto Login (credential stored in the App)
User Name | Plane Text | User Name | Plane Text | User Name | Plane Text
Password | Plane Text | Password | Plane Text | Password | Hash
Club Name | Plane Text | Club Name | Plane Text | Club Name | Plane Text
Password | Plane Text | Password | Plane Text | Password | Hash
LogAs | User | LogAs | UserOrClub | LogAs | Club
|  |  | ListedClub |  | UserOrClub
ListedClub

## Main Navi
Function | Sub-Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Impl. Days | Status | Comment
AppBar | Settings Icon Top-Right Corner |  | A |  | 1 | 2022-12-25 |  |  |  | Open
Bottom Panel | Account
Representation
Visibility

## Identity
Function | Sub-Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Impl. Days | Status | Comment
Register New User | API exists |  | A |  | 1 | 2022-12-25 | 2023-01-15 | 2023-02-15 |  | Done
Sign-in User from Sing-in Form | API exists | plain password | A |  | 1 | 2022-12-25 |  |  |  | Processing
Sign-in User at App Start | API exists | hashed password | A |  | 1 | 2022-12-25 | 2023-04-15 | 2023-04-30 |  | Done
Sign-in User in On-line mode |  | hashed password | A |  | 1 | 2022-12-25 |  |  |  | Processing
Change User Password |  |  | A |  | 1 | 2022-12-25 | 2023-02-20 | 2023-02-28 |  | Done
Change Email |  | Password shall not be used by other users | A |  | 1 | 2022-12-25 | 2023-02-25 | 2023-03-05 |  | Done
User Password Recover |  |  | A |  | 1 | 2022-12-25 | 2023-01-01 | 2023-01-20 |  | Done
Change User Avatar |  |  | C |  |  | 2022-12-25 |  |  |  | Processing
Personal Data Download |  |  | C |  |  | 2022-12-25 |  |  |  | Processing
Delete User | Mark user as deleted in DB |  | A |  | 1 | 2022-12-25 | 2023-03-10 | 2023-03-15 |  | Done

## Club
Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Days Impl | Status | Comment
Create Club |  | B |  |  | 2022-10-01 | 2023-03-01 | 2023-03-15 |  | Done
Sing-in Club from Sign-In Form |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 | 71 | Done
Sign-in Club at App Start |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 |  | Done
Sign-in Club Once switching to On-Line |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 |  | Done
Rename Club |  | A |  |  | 2022-10-01 |  |  |  | Open
Change Club Password |  | A |  |  | 2022-10-01 |  |  |  | Open
Join Club |  | A |  |  | 2022-10-01 | 2023-04-15 | 2023-04-30 |  | Done
Leave Club |  | A |  |  | 2022-10-01 |  |  |  | Open
Change Club Avatar |  | C |  |  | 2022-10-01 |  |  |  | Open | N/A for V4
Delete Club |  | B |  |  | 2022-10-01 |  |  |  | Open
Change Club Visibility |  | A |  |  | 2023-02-26 |  |  |  | Open
Add members to Club |  | C |  |  | 2023-02-26 |  |  |  | Open | N/A for V4
Remove members to Club |  | B |  |  | 2023-02-26 |  |  |  | Open
Set roles to members |  | B |  |  | 2023-02-26 |  |  |  | Open

## API BackEnd
Identity | Comment | Current Response Codes | Admin Block | SrvUsr Block | Test Normal | Test Corner | Locale
Register | Register a new user and a dedicated club | Ok / Conflict | N/A | N/A | Ok | Ok | Open
Login | Sing-in to the system as user or club | Ok / Unauthorized | N/A | N/A | Ok | Ok | Open
CheckUserNameFree | Checks if provided user name is free | Ok | N/A | N/A | Ok | Open | Open
ChangeUserPassword | Shall be requested by a user | Ok / Conflict | Open | Ok | Ok | Fail | Open
CheckEmailFree | Checks if provided email is free | Ok | N/A | N/A |  |  | Open
ChangeUserEmail | Shall be requested by a user | Ok / Conflict | Open | Ok
RequestUserPasswordReset | Shall be requested by a user | Ok / Conflict | Open | Ok |  | N/A | Ok
GetUserProfile | Shall be requested by a user | Ok / Conflict | Open | Open
DeleteUserProfile | Shall be requested by a user | Ok / Conflict | Open | Open
Club
CreateClub | Create a new club by a user request | Ok / Conflict | N/A | N/A
GetPublicClubs | Get the list of public clubs | Ok | N/A | N/A
CheckClubNameFree | Checks if provided club name is free | Ok | N/A | N/A
JoinClub | Shall be requested by a user | Ok / Conflict | Open | Open
GetClubDetails | Shall be requested by a user | Ok / Conflict
Checklist
ReadCheckList |  | Ok / Conflict / Unauthorized / NotFound

## Refactor
| Previous Type | New Type | Changes | Comment | Status
check username free | CheckUserNameFreeResult | CheckValueValidResponse | IsValueValid | Delete file after refactor | Open
check email free | CheckEmailFreeResult | CheckValueValidResponse | IsValueValid | Delete file after refactor | Open