## PI
PI Nr. | Story | In Date | Start Date | End Date | Impl. Days | Status | Comment | Carry-Over
PI 1 | Side / Drawer Menu Concept | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done | Think about large / very large screens | GetDateTime
| Shared Preferences Concept | 2022-12-25 | 2022-12-25 |  |  | Processing | Not working on Web | AboutDialog
| Settings Menu Concept | 2022-12-25 | 2023-01-03 |  |  | Processing |  | StartDialog
| User Management | 2022-12-25 |  |  |  | Open
| Club Management | 2022-12-25 |  |  |  | Open
| Light / Dark Mode Concept | 2022-12-25 | 2022-12-25 |  | -44920 | Processing | Colors set while theme set open
| Splash Screens | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done | Web is open
| Startup Warning Dialog | 2022-12-25 | 2022-12-28 | 2022-12-28 | 0 | Done
| Exit confirmation | 2022-12-25 | 2022-12-28 | 2022-12-28 | 0 | Done
| About Dialog | 2022-12-25 | 2022-12-26 | 2022-12-26 | 0 | Done | Font size depending on screen size open
| Github Repo | 2022-12-25

## Roles
| Root | Owner | Manager | Member
Create Club | X | X | X | X
Change Club Name | X | X | O | O
Change Club Visibility | X | X | O | O
Hand-over Club | X | X | O | O | If club has multiple owners, they shall confirm (process TBD)
Leave Club | O | O | X | X
Delete Club | X | X | O | O | If club has multiple owners, they shall confirm (process TBD)
Assign Owner | X | X | O | O
Unassign Owner | X | O | O | O
Assign Manager | X | X | O | O
Unassign Manager | X | X | O | O
Remove Manager | X | X | O | O
Invite Member | X | X | X | O
Remove Member | X | X | X | O
Create Checklist | X | X | X | O
Edit Checklist | X | X | X | O
Read Checklist | X | X | X | X | if visibility setting allows
Hand-over Checklist | X | X | X | O
Create Model | X | X | X | O
Edit Model | X | X | X | O
Read Model | X | X | X | X | if visibility setting allows
Hand-Over Model | X | X | X | O
Create Aircraft | X | X | X | O
Edit Aircraft | X | X | X | O
Read Aircraft | X | X | X | X | if visibility setting allows
Hand-over Aircraft | X | X | X | O

## Tech Debts
Function | Sub-Function | Debt | Prio | Complexity | API Ver | In Date | Start Date | End Date | Impl. Days | Status | Comment
Light / Dark Mode |  |  | B | normal |  | 2022-12-25 | 2022-12-26 |  | -44921 | Processing
Splash Screen | Web |  | B | normal |  | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Open
| Android 12+ |  | B | normal |  | 2023-01-14 |  |  | 0 | Processing
| IOS |  | B | normal |  | 2022-12-25 | 2022-12-25 | 2022-12-25 | 0 | Done
Get Current Date / Time |  | Move to future provider as stream | B | normal |  | 2023-01-14 | 2023-01-14 | 2023-01-14 | 0 | Done
Sig-in |  | Refactor Menu | B | normal |  | 2023-01-14 |  |  | 0 | Open
|  | Use-case if user is already signed in (user / club) | B | normal |  | 2023-01-14 |  |  | 0 | Done
Font Size in Widgets |  | Switch to Theme Style with delta Size | A | normal |  | 2023-01-14 | 2023-02-01 |  |  | Open
Routing to Sign-In |  | Go to Sign-in form in case of 401 response | B | normal |  | 2023-02-26 |  |  |  | Open
Tab order, skip icon button |  | Skip icon buttons for navigation in form | B | normal |  | 2023-02-26 |  |  |  | Processing

## Login Type
Register |  | Active Login |  | Auto Login (credential stored in the App)
User Name | Plane Text | User Name | Plane Text | User Name | Plane Text
Password | Plane Text | Password | Plane Text | Password | Hash
Club Name | Plane Text | Club Name | Plane Text | Club Name | Plane Text
Password | Plane Text | Password | Plane Text | Password | Hash
LogAs | User | LogAs | UserOrClub | LogAs | Club
|  |  | ListedClub |  | UserOrClub
ListedClub

## Main Navi
Function | Sub-Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Impl. Days | Status | Comment
AppBar | Settings Icon Top-Right Corner |  | A |  | 1 | 2022-12-25 |  |  |  | Open
Bottom Panel | Account
Representation
Visibility

## Identity
Function | Sub-Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Impl. Days | Status | Comment
Register New User |  |  | A |  | 1 | 2022-12-25 | 2023-01-15 | 2023-02-15 |  | Done
Sign-in User from Sing-in Form |  | plain password | A |  | 1 | 2022-12-25 |  |  |  | Done
Sign-in User at App Start |  | hashed password | A |  | 1 | 2022-12-25 |  |  |  | Open
Sign-in User in On-line mode |  | hashed password | A |  | 1 | 2022-12-25 |  |  |  | Open
Change User Password |  |  | A |  | 1 | 2022-12-25 | 2023-02-20 | 2023-02-28 |  | Done
Change Email |  | Password shall not be used by other users | A |  | 1 | 2022-12-25 | 2023-02-25 | 2023-03-05 |  | Done
User Password Recover |  |  | A |  | 1 | 2022-12-25 | 2023-01-01 | 2023-01-20 |  | Open
Change User Avatar |  |  | C |  |  | 2022-12-25 |  |  |  | Open
Personal Data Download |  |  | C |  |  | 2022-12-25 |  |  |  | Done
Delete User | Mark user as deleted in DB |  | A |  | 1 | 2022-12-25 | 2023-03-10 | 2023-03-15 |  | Done

## Club
Function | Conditions | Prio | Complexity | PI | In Date | Start Date | End Date | Days Impl | Status | Comment
Create Club |  | B |  |  | 2022-10-01 |  |  |  | Open
Sing-in Club from Sign-In Form |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 | 71 | Open
Sign-in Club at App Start |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 |  | Open
Sign-in Club Once switching to On-Line |  | A | increased |  | 2022-10-01 | 2022-10-01 | 2022-12-11 |  | Open
Rename Club | If Manager | A |  |  | 2022-10-01 |  |  |  | Open
Change Club Password | If Manager | A |  |  | 2022-10-01 |  |  |  | Open
Join Club | Password check | A |  |  | 2022-10-01 |  |  |  | Open
Leave Club | If Member | A |  |  | 2022-10-01 |  |  |  | Open
Change Club Avatar | If Manager | B |  |  | 2022-10-01 |  |  |  | Open
Delete Club | If Manager | B |  |  | 2022-10-01 |  |  |  | Open
Change Club Visibility | If Manager | A |  |  | 2023-02-26
Add members to Club | If Manager | B |  |  | 2023-02-26
Remove members to Club | If Manager | B |  |  | 2023-02-26
Set roles to members | If Manager | B |  |  | 2023-02-26